## POA&M
Assessment Name | Related Control ID | Related AO ID | Weakness ID | Weakness Description | POA&M ID | Mitigation Description | Identified Date | Target Completion Date | Actual Completion Date | Responsible | POA&M Status
CUI Enclave | 3.1.2 | 3.1.2[a] | WK-001 | The organization has not fully defined or standardized the types of transactions and functions that each user role is permitted to execute. As a result, users may have inconsistent or excessive access rights beyond what is necessary for their roles. This lack of clarity in access permissions can lead to unauthorized access to sensitive functions or transactions, increasing the risk of accidental or malicious misuse. | POA&M-001 | Define and Document Access Permissions by Role: Develop a clear and consistent access control policy that defines the types of transactions and functions allowed for each user role based on the principle of least privilege. Implement Role-Based Access Control (RBAC): Use RBAC systems to enforce and automate access permissions, ensuring that users can only perform actions appropriate to their roles. Regular Access Reviews and Audits: Conduct periodic access reviews and audits to verify that permissions align with defined policies and adjust access levels as needed to maintain compliance and minimize risk. | 2024-10-25 | 2024-10-23 | 2024-10-21 | Security | Completed
CUI Enclave | 3.1.4 | 3.1.4[b] | WK-002 | The organization has not effectively separated critical duties, resulting in some individuals having overlapping responsibilities that allow them to initiate, authorize, and complete sensitive transactions without oversight. This lack of separation increases the risk of fraud, errors, or malicious actions going undetected because one person can bypass internal controls. | POA&M-002 | Define Critical Roles and Responsibilities: Clearly define the roles and duties that require separation to prevent any single individual from having full control over sensitive processes. Implement Segregation of Duties (SoD) Controls: Establish SoD controls that ensure different individuals are responsible for initiating, approving, and executing key tasks, especially in financial, HR, or IT processes. Regular Review and Monitoring: Periodically review role assignments and access permissions to ensure that duties remain appropriately segregated, and monitor for any violations of separation. | 2024-10-25 | 2024-11-14 | 2024-11-21 | Security | In-Progress
CUI Enclave | 3.1.12 | 3.1.12[b] | WK-003 | The organization has not clearly defined the types of remote access methods that are permitted for use. As a result, employees may use a variety of remote access methods, some of which may be insecure or unauthorized (e.g., unsecured remote desktop access or unapproved VPN solutions). This inconsistency increases the risk of unauthorized access and compromises the overall security posture of the organization. | POA&M-003 | Establish a Remote Access Policy: Develop and document a policy that clearly defines the types of remote access methods that are permitted, such as VPNs, secure remote desktop tools, or multi-factor authenticated access. Standardize and Approve Remote Access Tools: Ensure that only approved remote access methods are used and implement technical controls to prevent unauthorized methods from being utilized. Educate Users on Approved Methods: Conduct training and awareness sessions to inform users about the approved remote access methods and the importance of following the organization's remote access policy. | 2024-10-25 | 2024-10-25 | 2024-10-26 | Security | Completed